## Sheet1
Project Status Check Report Team - 8
Sl no. | Employee ID | Name | Domain | Module | 2022-03-26 | 2022-03-28 | 2022-03-29 | 2022-03-30 | 2022-03-31 | 2022-04-01
1 | 2487269 | Shubham Sanjay Sapkal | Back-end | Admin, Login, Logout | Admin Detail | Admin | Login | Logout | Integration
2 | 2487614 | Sharath Kumar H R | Back-end | Customer, Customer Duty | Customer Detail | Customer | Customer duty Details | Customer Duty Details | Integration
3 | 2489249 | Sadana Nandini | Back-end | Engineer, Engineer Duty | Engineer Detail | Engineer Detail | Engineer | Engineer Duty Details | Integration | Swagger Tool, Postman Tool
4 | 2489315 | Talloju Anuradha | Back-end | Manager | Manager Details | Manager Details | Manager Details | Manager Duty Details | Integration
5 | 2487314 | S Tharani | Back-end | Feedback | Feedback Details | Feedback Details | Feedback Table | Feedback Table | Integration
6 | 2489288 | Shiva Gaini | Front-end | Admin | Admin Layout | Admin Component | Admin Dashboard | Admin Registration | Integration | image/Styling
7 | 2489324 | Thanneerupavan kumar | Front-end | Customer, Customer Complaint | Customer Layout | Customer Component | Customer Dashboard | Customer Registration | Integration | image/Styling
8 | 2488361 | Santhosh Sakthivel | Front-end | Engineers, Feedback, Header | Engineer Layout | Engineer Component | Engineer Dashboard | Engineer Registration | Integration | image/Styling
9 | 2489131 | Talakonda Ravi | Front-end | Manager | Manager Layout | Manager Component | Manager Dashboard | Manager Registration | Integration | image/Styling
10 | 2489513 | Shubham jawalkar | Front-end | Application Component | Application Layout | Application Components | Application Component | Feedback Customer | Integration | image/Styling